Tennessee’s Tiniest Babies:  Prevention of Severe Intraventricular Hemorrhage (sIVH)

A Tennessee Initiative for Perinatal Quality Care Collaborative

Inter-institutional Improvement Project

Project Development Leaders

Scott Guthrie, MD

State Project Leader & TIPQC Infant Medical Director

Marcelo Rains, MD

State Project Leader

Parul Zaveri, MD

State Project Leader

Patricia A. Scott, DNP, APRN, NNP-BC, C-NPT

TIPQC Infant Quality Improvement Specialist

Brenda Barker, MEd, MBA

TIPQC Executive Director

Theresa A Scott, MS

TIPQC Data Manager

Rolanda Lister, MD

TIPQC Health Equity Officer

Overview

We are seeking to lower Tennessee’s infant mortality rate to 5 deaths per 1,000 live births by focusing on the implementation of potentially better practices which can improve the survival rates and the outcomes of preterm infants born at less than 29.6 or less weeks gestation.

The development and implementation of the “Tennessee's Tiniest Babies'' (TTB) project will occur from Q3 2022 to Q3 2025.  The project has been developed and will be launched in phases determined by specific care bundles – see Figure 1.  The intent is to have participating hospitals implement the care bundles cumulatively – incorporating the potentially better practices from each bundle into their unit. This toolkit is focused on the severe Intraventricular Hemorrhage (sIVH) care bundle. The project is proposed to end in Q4 2026.

This quality improvement project will be carried out in individual hospitals with collaborative coordination through the Tennessee Initiative for Perinatal Quality Care (TIPQC).

Background

Preterm birth is a multi-factorial problem that, despite national and state efforts remains relatively unchanged1 2.  Specifically, an increase in the number of the earliest preterm births (infants with birth weights of <750 g and gestational age of <28 weeks) has been implicated as the primary contributor to infant mortality rates3.   Very preterm births, defined as <32 weeks and birth weight <1500g, represented 33% of all infant deaths in one

report. In this study, more than two thirds of deaths attributable to preterm birth occurred during the first day of life and 27% of deaths occurred within the next 27 days 4.

Variation in outcomes among NICUs have also been reported5 6 7.  Practice variation, even amongst providers in the same group, can be a contributing factor to these varied outcomes8 9.  We have fortunately witnessed significant progress in the care of preterm infants over the past few decades. These advances have gradually moved from new technologies and medicines to how we care for these infants. This has led to improved survival rates and outcomes by the centers who have focused on improving the delivery of care¹0.

Preliminary Data from Tennessee and Evidence of a Performance Gap

Tennessee has thirteen level 3 and 4 NICUs across the state who care for infants <32 weeks and a birth weight <1500g. In 2020, 1,352 babies, or 1.7% of live births, were born very preterm in Tennessee and cared for at these facilities11.  Statistically, this group of infants represents approximately one-third of our state’s infant deaths which include disparities amongst racial and ethnic groups.  To lower Tennessee’s infant mortality rate, meet the goal as put forth in the “2030 Healthy People” objectives, and improve equity by reducing disparities in care, a collaborative approach to the care along with the implementation of effective care strategies for Tennessee’s Tiniest Babies should be undertaken.

Rationale for TIPQC Improvement: Many state collaboratives have worked on decreasing the rate of severe intraventricular hemorrhage in their respective states.  Tennessee has not yet worked on this area of improvement. With state support, education, monthly huddles, learning sessions and data capture, teams should be able to better adopt potentially better practices.  These potentially better practices will improve care for Tennessee’s Tiniest Babies.

Project Design

Each participating facility/team will:

- Hold regular, at least monthly, team meetings.

- Regularly review and revise your goals, current system, opportunities for improvement, and barriers.

- Plan and conduct tests of the recommended changes detailed in this toolkit.

- After successful testing and adaptation, implement the changes in your facility.

- Attend and actively participate in the monthly huddles, quarterly learning session, and annual statewide meetings.

- Capture and submit the defined project data as required (with minimal to no data lag).

- Submit a monthly report that includes data as well as information on changes being tested and/or implemented.

- Strive to achieve the project aim and the project’s process and structure measure goals:

  - At least 90% compliance on all defined process measures.

  - Have all structures (defined by the structure measures) in place by the end of the project.

Aim

- To reduce the mortality in infants less than or equal to 29.6 weeks gestational age by 25% of the Tennessee state baseline. There should be a dose response effect seen with the implementation of bundles which address broader global aims.

The aim of this sIVH care bundle is:

- 25% relative reduction (over last 3 years institutional baseline) in severe intraventricular hemorrhage (Grade III & IV) in infants less than or equal to 29.6 weeks gestational age in participating TN NICUs by March 2024

The proposed aims of the forthcoming care bundles are:

- 25% relative reduction (over last 3 years institutional baseline) in chronic lung disease in infants less than or equal to 29.6 weeks gestational age in participating TN NICUs by September 2024

- 25% relative reduction (over last 3 years institutional baseline) in necrotizing enterocolitis in infants less than or equal to 29.6 weeks gestational age in participating TN NICUs by March 2025

- 25% relative reduction (over last 3 years institutional baseline) in hospital acquired infections in infants less than or equal to 29.6 weeks gestational age in participating TN NICUs by September 2025

Charter

Tennessee’s Tiniest Babies:  Prevention of Severe Intraventricular Hemorrhage was selected by an interdisciplinary team of Tennessee neonatal care providers.  Units representing multiple Tennessee perinatal regions indicated their willingness to fully participate in the project if implemented on a statewide basis.  By completing the project application, each participating unit agrees to fully implement the project as designed, collect and submit the required monthly data in a timely manner, and participate in monthly webinars and statewide face-to-face meetings.

Toolkit

For this project, the Tennessee’s Tiniest Babies:  Prevention of Severe Intraventricular Hemorrhage Tool Kit (2022) was written by experts in neonatal care from across the state.  The

information within the tool kit was developed using the most recent evidence.  A comprehensive reference list for further reading is included.

Measures

Target population: Infants born 29.6 or less weeks gestation admitted to one of the participating NICUs for care. This includes all infants including transfers admitted within 24 hours of birth.

- Outcome measures:

#1. Percent severe intraventricular hemorrhage (sIVH)) (among targeted infants)

- Grade 3 or 4 IVH confirmed by head ultrasound (HUS) on or before Day 14 of life

#2. Percent mortality by hospital discharge or 40 weeks corrected gestational age, whichever comes first  (among targeted infants)

Both these Outcome measures will be calculated from the captured “TIPQC TTB-sIVH PROJECT CLINICAL CARE CHECKLIST” records – see “Data Collection” below.

Baseline data:

- Participating NICUs will retrospectively capture and report annual mortality and annual severe IVH rates (both among the target population) for the 3 years prior to the project start (2019, 2020, and 2021).

- This baseline data will serve as the “institutional baseline” from which they are trying to improve (planned 25% reduction)

- Process Measures:

- Percent of mothers (of targeted infants)  receiving at least 2 doses of antenatal steroids

- Percent of mothers (of targeted infants)  receiving Magnesium Sulfate (MagSO4)

- Percent of targeted infants with cord clamped at least 60 seconds after birth

- Percent of targeted infants receiving Indomethacin within first 24 hours of life

  - Among those targeted infants that qualify for administration of Indomethacin (<25 completed weeks gestation;  or 25-27 completed weeks gestation and outborn; or 25-27 completed weeks gestation and their mother did not receive 2 doses of antenatal steroids)

- Percent of targeted infants receiving ≥1 normal saline boluses within first 72 hours of life

- Percent of targeted  infants receiving any vasopressors within first 72 hours of life

- Percent of targeted infants receiving Sodium Bicarbonate within first 72 hours of life

These Process measures will be calculated from the captured “TIPQC TTB-sIVH PROJECT CLINICAL CARE CHECKLIST” records – see “Data Collection” below.

In addition, participating NICUs will report the following Process measures quarterly:

- Provider education

  - Cumulative proportion of providers, including Neonatologists and NNPs, who have completed an education program on sIVH Prevention that includes the unit-standard protocols

    - Report estimate in 10% increments (0-9%, 10-19%, 20-29%, 30-39%, 40-49%, 50-59%, 60-69%, 70-79%, 80-89%, 90-100%)

- Nursing education

  - Cumulative proportion of neonatal nurses who have completed an education program on sIVH Prevention that includes the unit-standard protocols

    - Report estimate in 10% increments (0-9%, 10-19%, 20-29%, 30-39%, 40-49%, 50-59%, 60-69%, 70-79%, 80-89%, 90-100%)

- Balancing Measures:

- Percent of targeted infant with 5-minute APGAR score ≤ 3

- Percent of  hypothermic targeted infants on first temperature

- Percent of  hypothermic targeted infants on admission to NICU

- Percent of targeted infants with any gastrointestinal (GI) perforations (including SIP and NEC) within first 7 days of life

These Balancing measures will be calculated from the captured “TIPQC TTB-sIVH PROJECT CLINICAL CARE CHECKLIST” records – see “Data Collection” below

Data Entry

Participating teams (teams from institutions that have completed the Data Use Agreement, the Project Application, and required TDH computer access forms) will complete data entry training provided by TIPQC.  Team members identified in the project application will be granted access to the project’s REDCap data resources, and enter data for this QI project through the REDCap system.  Details of the system, data handling and security, compliance and oversight measure

are specified in the TIPQC Framework protocol and the TIPQC Participation and Data Use Agreement.  No changes in data management are anticipated.

QI Data Reports

The various types of periodic reports utilized for this project may include:

- A report consisting of only your local facility’s/center’s data.  You will not be able to download or see other participating center’s local reports, nor will other participating

centers have access to your local report.  You will use this report to present your facility’s/center’s performance at each monthly huddle.

- A report comparing the performance of your local facility/center to the performance of the other participating teams.  The other participating teams will be de-identified in this report.

- A report consisting of aggregate data from the collaborative as a whole.  The TIPQC state leaders will present this report at each monthly huddle to share the overall performance of all of the participating facilities/centers.  This report will only be available to TIPQC state leaders.

- A confidential report that compares the overall performance of all of the participating teams.  The participating teams will be identified in this report and thus will contain sensitive content.  This report will only be made available to the TIPQC state leaders for coaching and improvement purposes.

The core contents of the periodic reports will be determined by group consensus, but flexibility is available to modify the reports as needed over the course of the project.

Record Retention

Record retention described in the TIPQC Framework protocol will be followed.

Recruitment of participating centers

The recruitment strategy described in the TIPQC Framework protocol will be used.

Procedures for participating centers

The data procedures described in the TIPQC Framework protocol will be used.  From the protocol, “Each team will be encouraged to develop procedures to support project implementation, data reporting, and change analysis by the local project team.  Substantial local latitude is provided to allow flexibility for integration of TIPQC activities into local workflow and schedules, though a minimum frequency and timeliness of data entry is required and is outlined in the project application and data agreement.   In this all-voluntary collaborative, multiple data reporting systems and paradigms will be supported to facilitate the broadest possible participation.”

Training plan for participating centers

No changes in the training plan outlined in the TIPQC Framework protocol are anticipated for this QI project.

Duration of the project

The duration of the project is 12 months.  Participants or the TIPQC membership at large may ask the Oversight Committee to extend the project or use it as a building block for future projects with complimentary endpoints.

Role of the TIPQC Oversight Committee

The critical role of the TIPQC Oversight Committee is not anticipated to change during this QI project.  From the protocol: “Throughout the selection, development, pilot testing, and implementation of a project the TIPQC Oversight Committee plays a vital role.  The Committee oversees the selection process at the state meeting and is tasked with ensuring that stakeholders who are present have the opportunity to contribute to the selection process.  Following project development and pilot testing, the pilot toolkit is reviewed and approved by the Oversight Committee.   Upon completion of pilot testing and incorporation of pilot directed modifications, the Oversight Committee reviews and approves the final toolkit for release to potential participants.”

“Throughout all phases of the project, the Oversight Committee will be informed of any concerning trends in balancing measures and of any potential safety issues.  Further the Oversight Committee is empowered to halt any quality improvement project at any time.   A project will be stopped if a simple majority of the entire Oversight Committee votes to halt the project.  Should a majority of the Oversight Committee vote to stop a project, a message will be sent to all participating centers directing them to stop the project and data collection will be suspended.  The message will include both a detailed explanation of the Committee’s concerns and a roll call listing of Committee member’s votes- yes, no, abstain, or not present.  Given the multiple levels of evidence-based review employed prior to statewide release of the toolkit, early termination of a project by the Oversight Committee is not expected, but a formal mechanism is included should events arise that warrant pausing or halting project participation.

Finally, the Oversight Committee controls extensions of project duration, or changes in progress scope.  The Oversight Committee is charged with balancing the cost vs. value of any proposed extension or change within the confines of the resources and mission of TIPQC.  The Oversight Committee may vote, again by simple majority, to extend project duration or scope or opt to extend the project until the next state meeting for a general membership vote.”

References

1Gupta, R. & Froeb, K. (2020).   Preterm birth.   The Journal of Perinatal & Neonatal Nursing, 34(2), 99-103. doi: 10.1097/JPN.0000000000000469

2March of Dimes. Preterm Birth: Tennessee, 2010-2020. March of Dimes. Retrieved July 6, 2022, from https://www.marchofdimes.org/peristats/data?reg=99&top=3&stop=60&lev=1&slev=4&obj=1&sreg=47

3MacDorman, M. F., Martin, J. A., Mathews, T. J., Hoyert, D. L., Ventura, S. J. (2005).  Explaining the 2001–02 infant mortality increase: Data from the linked birth/infant death data set. Natl Vital Stat Rep., 53(12), 1–22.

4Callaghan, W. M., MacDorman, M. F., Rasmussen, S. A., Qin, C., & Lackritz, E. M. (2006). The contribution of preterm birth to infant mortality rates in the United States. Pediatrics, 118(4), 1566–1573. https://doi.org/10.1542/peds.2006-0860

5Horbar, J. D., Badger, G. J., Lewit, E. M., Rogowsk,i J., & Shiono, P. H.  (1997).   Vermont Oxford Network. Hospital and patient characteristics associated with variation in 28-day mortality rates for very low birth weight infants. Pediatrics, 99(2), 149–156.

6Lee, S. K., McMillan, D. D., Ohlsson, A., & et al. (2000).  Variations in practice and outcomes in the Canadian NICU network: 1996-1997. Pediatrics, 106(5), 1070–1079.

7Vohr, B. R., Wright, L. L., Dusick, A. M., & et al.  (2004).  Neonatal Research Network. Center differences and outcomes of extremely low birth weight infants. Pediatrics, 113(4), 781–789.

8Institute of Medicine - Committee on Quality of Health Care in America. (2001).  Crossing the quality chasm: A new health system for the 21st century.  National Academies Press.

9Aziz, K., McMillan, D. D., Andrews, W., & et al.  (2005).  Canadian Neonatal Network. Variations in rates of nosocomial infection among Canadian neonatal intensive care units may be practice-related. BMC Pediatr., 5(1), 22–34.

10Bell, E. F., Hintz, S. R., Hansen, N. I., Bann, C. M., Wyckoff, M. H., DeMauro, S. B., Walsh, M. C., Vohr, B. R., Stoll, B. J., Carlo, W. A., Van Meurs, K. P., Rysavy, M. A., Patel, R. M., Merhar, S. L., Sánchez, P. J., Laptook, A. R., Hibbs, A. M., Cotten, C. M., D'Angio, C. T., Winter, S., & et al.  (2022).  Eunice Kennedy Shriver National Institute of Child Health and Human Development Neonatal Research Network.  Mortality, in-hospital morbidity, care practices, and 2-year outcomes for extremely preterm infants in the US, 2013-2018. JAMA, 327(3), 248–263. https://doi.org/10.1001/jama.2021.23580

11March of Dimes. Infant Mortality Rates: Tennessee. Retrieved July 6, 2022, from https://www.marchofdimes.org/peristats/

Appendices

- TIPQC Participation and Durable Data Use Agreement (TIPQC Participation and Durable Data Use Agreement.pdf)

- TIPQC Project Application

- Redcap data entry tool